## OLPCoprs Gantt Chart
Project Plan - task list | Ownership | Duration | Start Date | End Date | % Complete | Hours | Cost | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1st-30th | 1st-30th | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
[8 empty] | February |  |  |  | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | August | September | [59 empty] | October
Application Period
Project Proposal
Organize OLPCorps Team |  |  | 2009-03-01 | 2009-03-27 | [7 empty] | Organize OLPCorps Team
Find technical lead |  |  | 2009-03-01 | 2009-03-27 | [7 empty] | Find Technical Team
Partner with NGO/School |  |  | 2009-03-01 | 2009-03-27 | [7 empty] | Partner with NGO/School
Receive Letter(s) of Support |  |  | 2009-03-01 | 2009-03-27 | [7 empty] | Receive Letter(s) of Support
Publish draft project proposal on wiki |  |  | 2009-03-01 | 2009-03-27 | [7 empty] | Publish Project Proposals on Wiki
Subscribe to Corps listserve |  |  | 2009-03-01 | 2009-03-27 | [7 empty] | Subscribe to Corps List Serve
Draft budget |  |  | 2009-03-01 | 2009-03-27 | [7 empty] | Draft Budget
Request OLPC Endorsement Letter for any grants |  |  | 2009-03-01 | 2009-03-27 | [7 empty] | Request OLPCorps Letter of Endorsement
Submit Project Proposal to OLPCorps@laptop.org |  |  | 2009-03-01 | 2009-03-27 | [7 empty] | Submit Project Proposal
Post-Acceptance Period
Immediate Logistical Requirements
Send OLPCorps 1 paragraph biography of each member |  |  | 2009-04-10 | 2009-04-20 | [47 empty] | Collect Bios
Send OLPCorps copies of: passport, visas, immunizations |  |  | 2009-04-10 | 2009-04-20 | [47 empty] | Collect doc. copies
Have university rep (e.g. Dean) verify student status by emailing OLPCorps |  |  | 2009-04-10 | 2009-04-20 | [47 empty] | Confirm student status
Send flight details to OLPCorps so itineraries can be purchased |  |  | 2009-04-10 | 2009-04-20 | [47 empty] | Collect flight details
Send personal addresses to OLPCorps so 1 XO can be shipped |  |  | 2009-04-10 | 2009-04-20 | [47 empty] | Collect personal addresses
Send OLPCorps type of charger needed (EU or USA) after confirming with school and NGO |  |  | 2009-04-10 | 2009-04-20 | [47 empty] | Identify type of charger needed
Finalize shipping logistics (XO's and bundle) with OLPCorps team & local partner |  |  | 2009-04-10 | 2009-04-20 | [47 empty] | Finalize shipping logistics
Promotion - raise awareness of OLPC and local community
University Promotion via student newspapers |  |  | 2009-04-10 | 2009-10-31 | [47 empty] | University Promotion via Student Newspapers
Promotion to personal networks |  |  | 2009-04-10 | 2009-10-31 | [47 empty] | Promotion to Personal Networks
Promotion in local town/city newspapers |  |  | 2009-04-10 | 2009-10-31 | [47 empty] | Promotion to local town press
Design long-term promotion strategies |  |  | 2009-04-10 | 2009-10-31 | [47 empty] | Design long-term promotion strategy
Finances
Fundraising Kit |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Fundraising Kit tailored to OLPCorps Team
Learn how-to sheet on using OLPC's 501c3 status |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Learn how to use 501c3
Grant resources, fundraising ideas, tips -- publish on wiki for other teams |  |  | 2009-04-10 | 2009-08-31 | [47 empty] | Publish Fundraising Efforts on Wiki: Best practices
Draft Budget & share with OLPCorps Team |  |  | 2009-04-10 | 2009-04-20 | [47 empty] | Draft Budget and Share with OLPC
Learning
Online seminars (technical) |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Online Seminar - technical
Online seminars (learning, lessons plans, projects) |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Online Seminar - learning
Online seminars (General Qs) |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Online Seminar - General Questions/Concerns
Online seminars (wiki) |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Online Seminar - Wiki: How to
Design project ideas with the OLPC Learning Team and OLPCorps Teams |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Project Ideas
Suggested academic readings online |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Academic Readings
Each team member has learned to edit wiki |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Learn how to use wiki
Development
Hold meetings with local school and NGO to set expectations & finalize plans |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Plan meetings and phone conferences with local schools and partnering organizations to finalize plans
Participate in OLPCorps-Student Team online conference |  |  | 2009-05-04 | 2009-05-08 | [68 empty] | Phone Conf's
Blog |  |  | 2009-04-10 | 2009-10-31 | [47 empty] | Blog about experiences
As needed, provide feedback on OLPCorps as a program: improvements, etc. |  |  | 2009-04-10 | 2009-10-31 | [47 empty] | Provide feedback on OLPCorps Program
Power
Discuss existing power infrastructure with school and NGO |  |  | 2009-04-10 | 2009-04-20 | [47 empty] | Power infrastructure
Discuss alternative power options (if necessary) with OLPCorps team |  |  | 2009-04-10 | 2009-04-20 | [47 empty] | Alternative Power Options
Connectivity, Networking, & Internet
Discuss connectivity, networking, & Internet infrastructure plans with OLPCorps |  |  | 2009-04-10 | 2009-06-07 | [47 empty] | Discuss connectivity, networking, and internet plans with OLPCorps
Rwanda
Training
Depart to Kigali, Rwanda |  |  | 2009-06-06 | 2009-06-08 | [104 empty] | Arrive
Workshop |  |  | 2009-06-09 | 2009-06-17 | [106 empty] | Workshop
Depart from Kigali, Rwanda |  |  | 2009-06-17 | 2009-06-19 | [115 empty] | Depart
Deployment Stage
Deployment
Arrange to pick up XOs from customs, UNDP, etc |  |  | 2009-05-15 | 2009-06-20 | [82 empty] | Arrange to pick up XOs and bundle from local customs
Compile stories, multimedia, etc |  |  | 2009-06-17 | 2009-08-31 | [118 empty] | Compile Media
Blog weekly |  |  | 2009-06-17 | 2009-08-31 | [118 empty] | Blog
Implement Project Ideas |  |  | 2009-06-17 | 2009-08-31 | [118 empty] | Implement Project Ideas
Reflect and document on Project Ideas |  |  | 2009-06-17 | 2009-08-31 | [118 empty] | Reflect and document on Projects
Power
Implement chosen power system |  |  | 2009-06-17 | 2009-07-01 | [118 empty] | Implement power system
Identify changes/improvements to long-term power infrastructure |  |  | 2009-06-17 | 2009-08-31 | [118 empty] | Identify optimal long-term power infrastructure
Connectivity, Networking, & Internet
Set up School Server |  |  | 2009-06-17 | 2009-07-01 | [115 empty] | Set up school server
Set up Internet |  |  | 2009-06-17 | 2009-07-01 | [115 empty] | Set up Internet
Set up Access Point(s) | [119 empty] | Set up access points
Design
Meet with community stakeholders to discuss long-term sustainability |  |  | 2009-06-17 | 2009-08-31 | [118 empty] | Meet with community stakeholders
Identify potential expansions of deployment |  |  | 2009-06-17 | 2009-08-31 | [118 empty] | Identify potential expansions
Post-Deployment Stage
MIT/OLPC Conference
Send in flight details to OLPCorps for team representative |  |  | 2009-09-01 | 2009-09-14 | [131 empty] | Arrange Flights
Arrive to Boston |  |  | 2009-10-09 | 2009-10-10 | [169 empty] | Arv.
OLPCorps Conference |  |  | 2009-10-10 | 2009-10-11 | [170 empty] | Conf
Depart from Boston |  |  | 2009-10-12 | 2009-10-13 | [172 empty] | Dep.
Support
Support deployment via Corps Teams |  |  | 2009-08-31 | [132 empty] | Support Your Deployment